Nathaniel Medina

TLIM 3355 – Project Management Principles

9/8/2026

Homework 1

Version 1.0

- Research: Existing Parking Solutions

  - ParkMobile

  - ParkWhiz

  - SpotHero

  - ParkHouston

  - Parking.com

    - How will our app be different:

      - We will have a full interactable map that includes live updates on availability

      - Our app will have real time tracking for how long your vehicle has and will be allowed to park

      - A reservation system with built in digital payment

      - A dashboard that allows users to see availability within their range and even pricing

      - Finally we’ll have privacy controls and of course city compliance

- Vision & Scope:

How This Project Was Acquired:

$oftware ¢orp was contracted by Houston to create a modern parking management system that brings together all available parking in Houston. We have a reputation for creating large-scale and reliable software, which is why Houston has chosen us.

Company Introduction:

Here at $oftare ¢orp, we have an endless budget and resources at our disposal. Not only that, but we have extensive experience in software development and amazing teams all over the board.

Project Vison:

The Smart Parking Platform will provide real time availability and reduce congestion inside parking garages/areas. This system will be supported on both web and mobile devices and have navigation services.

Project Scope:

- Real-time availability

- Interactive map

- Reservation and payments

- Operator dashboard (for updates and local parking nearby with pricing)

- Analytics and reporting

- Notifications and alerts

- API integration

Out of Scope:

- Hardware installation (cameras, sensors)

- Vehicle identification system

- SRS Draft:

- Software Requirements Specification

- Project: Smart Parking Platform

- Version 1.0

- Date: 9.08.2026

- 1. Introduction:

  - 1.1 Purpose

  - This document defines the requirements for Smart Parking Platform

- 1.2 Scope

  - This application will be able to provide real-time availability for users, an interactive map, a way to reserve spots and pay for them, and an operator dashboard for local spots and prices. We will also provide analytics and reports, notifications/alerts, and API integration

- 2. Overall Description

- -Users: Houston drivers, city transportation staff, workers, tourist

- -System Environment: Web-based and mobile applications

- -Constraints: City privacy laws, third party APIs, fixed semester timeline

- -Assumptions: Internet connection, GPS availability, and mobile device compatibility

- 3. Functional Requirements

- FR1: The system shall allow users to register and log in securely.

- FR2: The system shall display real-time availability for parking

- FR3: The system shall have an interactive map

- FR4: The system shall allow user to reserve spots

- FR5: The system shall process digital payments and process recipes

- FR6: The system shall send notification and alerts about time remaining

- FR7: The system shall provide an operator dashboard for local spots/updates

- FR8: The system shall generate analytics for the user

- 4. Non-Functional Requirements

- NFR1: The system shall support at least 250,000 concurrent users

- NFR2: The system shall update the map availability within 1 – 3 seconds

- NFR3: The system shall provide 99% uptime

- NFR4: The system shall process payments within 5 seconds

- NRF5: The system shall comply with city privacy and law

- 5. Use Case Example

- Title: Reserve Parking Spot

- Actor: Driver

- Precondition: User is logged in and GPS active

- Steps:

  - 1. User opens the map

  - 2. User finds vacant spot

  - 3. User reserves spot

  - 4. User pays

  - 5. System payment goes through

- Postcondition: Reservation is stored and visible

15 Use Case Examples:

1. Account creation

Actor: Driver

Precondition: User has not created an account

Steps:

- User opens app

- User clicks “Create Account”

- User enters information

- Systems takes data

- System creates an account

Postcondition: User now has an account

2. Login

Actor: Driver

Precondition: User has an existing account

Steps:

- User opens login screen

- User enters username and password

- System accepts data

Postcondition: User is logged in

3. View real-time availability

Actor: Driver

Precondition: User is logged in

Steps:

- User selects “Find Parking”

- System retrieves data and updates

- System displays available spaces nearby

Postcondition: User sees available spots

4. Use interactive map

Actor: Driver

Precondition: User is logged in
Steps:

- User opens map

- System loads parking spots

- System displays available parking spots

Postcondition: Users sees map with available parking

5. Reserve Parking Space

Actor: Driver

Precondition: User is logged in and available spots nearby

Steps:

- User selects parking spot

- Users selects time slot

- User confirms reservation

- System processes reservation

Postcondition: User reservation is stored

6. Digital payment

Actor: Driver

Precondition: User has a reservation

Steps:

- User selects payment method

- User enters payment details

- System processes payment

- System confirms transaction

Postcondition: Payment is completed

7. Receiving Notifications

Actor: Driver

Precondition: User has notifications active, has active reservation

Steps:

- System registers start time

- Systems send notification to user

Postcondition: User receives alert about time left

8. View Reservation History

Actor: Driver

Precondition: User is logged in

Steps:

- User opens “History”

- System retrieves past reservations in the past 90 days

- System displays list

Postcondition: User sees reservation history

9. Navigate to Parking Location

Actor: Driver

Precondition: User has a reservation

Steps

- User selects “Navigate”

- Systems opens navigation

- Directions are displayed

Postcondition: User is routed to location

10. View Occupancy Dashboard

Actor: Parking Management

Precondition: Parking Management is logged in

Steps

- Parking Management opens dashboard

- System retrieves occupancy data

- System displays analytics report

Postcondition: Parking Management sees real-time occupancy

11. Adjust Pricing

Actor: Parking Management

Precondition: Parking Management is logged in

Steps:

- Parking Management opens pricing settings

- Parking Management enters new pricing

- System prices update

Postcondition: New pricing is set

12. Generate Analytics Report

Actor: Parking Management

Precondition: Parking Management is logged in

Steps:

- Parking Management selects “Generate Report”

- System complies data

- System displays report

Postcondition: Parking Management receives report

13. Manager User Accounts

Actor: Admin

Precondition: Admin is logged in

Steps:

- Admin opens user management

- Admin selects user(s)

- Admin updates or modifies account

Postcondition: User account is updated

14. Configure System Settings

Actor: Admin

Precondition: Admin is logged in

Steps:

- Admin opens system settings

- Admin adjust configuration in settings

- System save changes

Postcondition: System settings get updated

15. Review Pay Logs

Actor: Payment Manager

Precondition: Payment Manager is logged in

Steps:

- Manager opens payment logs

- System retrieves transaction data

- System displays logs for manager

Postcondition: Manager revises payment history

Nathaniel Medina

TLIM 3355 – Project Management Principles

09/17/2026

Homework 2

Version 1.1

1. Work Breakdown Structure (WBS)

Smart Parking Platform – 3 Level Deep Structure

1. Authentication

1.1 Registration

1.1.1 Input validation

1.1.2 Account creation

1.1.3 Email/Message verification

1.2 Login

1.2.1 Credential verification

1.2.2 Session creation

1.2.3 Password reset

1.3 Session Management

1.3.1 Token generation

1.3.2 Auto logout

1.3.3 Multi-device handling

2. User & Operator Management

2.1 User Profiles

2.1.1 View profile

2.1.2 Edit profile

2.1.3 Delete profile/account

2.2 Operator Accounts

2.2.1 Create operator account

2.2.2 Assign garage

2.2.3 Permissions setup

2.3 Role Management
		2.3.1 Driver role

2.3.2 Operator role

2.3.3 Admin role

3. Parking & Garage Management

3.1 Garage Setup

3.1.1 Add garage

3.1.2 Edit garage details

3.1.3 Remove garage

3.2 Spot Monitoring

3.2.1 Real-time occupancy tracking

3.2.2 Update parking spot status

3.2.3 Error handling

3.3 Interactive Map

3.3.1 Map rendering

3.3.2 Spot availability overlay

3.3.3 GPS integration

4. Reservation & Payment

4.1 Reservation System

4.1.1 Select spot

4.1.2 Choose time/duration

4.1.3 Confirm reservation

4.2 Payment Processing

4.2.1 Process payments

4.2.2 Receipt generator/generation

4.2.3 Refund/cancellation integration

4.3 Notifications

4.3.1 Time remaining alerts

4.3.2 Expiration warnings

4.3.3 Payment confirmation

5. Reporting & Analytics

5.1 Occupancy Reports

5.1.1 Daily occupancy reports

5.1.2 Peak hours

5.1.3 Garage comparison

5.2 Financial Reports

5.2.1 Revenue summary

5.2.2 Payment logs

5.2.3 Export payment summary

5.3 System Analytics

5.3.1 Usage trends

5.3.2 Error logs

5.3.3 Basic system performance report

2. Timeline/Gantt Chart:

Project Duration: 16 weeks

Timeline:

Week 1-3: Requirements/Planning

- Define project goals

- Identify core features

- Outline any constraints and assumptions

Week 3-5: Design

- Create basic UI sketches/designs

- Plan databases structure

- Map out system flow

Week 5-7: Development

- Build authentication

- Implementation of parking/reservation features

- Add payment/notifications

Week 7-9: Integration

- Connect all modules together

- Ensure main user flows work end-to-end

- Fix issues cause by combining features together (minor bug fixes)

Week 9-11: System Validation

- Check data accuracy (spot reservations/times, ensure data is updating properly)

- Test loading and simple performance

- Confirm features work as intended

Week 11-13: Beta/Risk Testing

- Run user testing on core features

- Find bugs and errors

- Apply fixes and stability

Week 13-16: Final Checks/Release

- Polish UI and navigation

- Polish any core/side features

- Release and monitor

Milestones:

- Requirements completed (end of week 3)

- Design approved (end of week 5)

- Core features built (end of week 9)

- System integrated (end of week 11)

- Validation passed (end of week 13)

- Beta testing complete (end of week 15)

- Final release ready/initial release (end of week 16)

Gantt Chart:

|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Require./Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| System Valid. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Beta/Risk Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Checks/Rel. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Nathaniel Medina

TLIM 3355 – Project Management Principles

09/24/2026

Homework 3

Version 1.2

Trello Board:

Added needed information for my Trello board and posted necessary screenshots to my GitHub Public Repo.

Nathaniel Medina

TLIM 3355 – Project Management Principles

10/1/2026

Homework 4

Version 1.3

16 Risks for Technical, Schedule, Financial, and People:

Risk By Category:

Technical Risk:

- Sensor API Instability

- Backend Integration Failures

- Map Rendering Performance Issues

- Security Vulnerabilities

Schedule Risks:

- Backend Delays

- UI Redesign Requests

- Dependency Bottlenecks

- Team Availability Issues

Financial Risks:

- Unexpected Costs

- Server Hosting Expenses

- Hardware Costs

- Additional Team Member Costs

People Risk:

- Team Member Turnover

- Skills Gaps

- Poor Communication

- Low Morale/Drive

Risk Register Table

| ID | Description | Probability (1 – 5) | Impact (1 – 5) | Score | Response Strategy | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Sensor Instability | 4 | 4 | 16 | Mitigate | Backend Lead | Add fallback sensor data |
| 2 | Backend Integration Failure | 3 | 5 | 15 | Mitigate | Full-stack Dev | Test in staging |
| 3 | Backend Delays | 4 | 3 | 12 | Accept | PM | Adjust sprint workload |
| 4 | UI Redesign Requests | 3 | 3 | 9 | Mitigate | UI/UX | Freeze Changes After Sprint 2 |
| 5 | Unexpected API Costs | 3 | 4 | 12 | Transfer | Finance | Move To Cheaper Tiers |
| 6 | Server Hosting Overages | 2 | 4 | 8 | Mitigate | DevOps | Enable Autoscaling Limits |
| 7 | Team Member Turnover | 2 | 5 | 10 | Accept | PM | Document Tasks |
| 8 | Skill Gaps | 3 | 3 | 9 | Mitigate | Team Lead | Provide Training |
| 9 | Security Vulnerabilities | 3 | 5 | 15 | Mitigate | Security Lead | Add Validation |
| 10 | Dependency Bottlenecks | 4 | 2 | 8 | Accept | Backend Lead | Monitor API Uptime |

Communication Plan

1. Meeting Times

Daily Update:

- Duration: 10 – 15 minutes

- Purpose: Quick sync on progress and blockers

- Attendees: Developers, UI/UX, Backend and PM

- Format:

  - What was done yesterday

  - What will be done today

  - Any blockers

Week Progress Meetings

- Duration: 30 – 45 minutes

- Purpose: Review sprint progress, adjust workload

- Attendees: Full team + Product Owner

- Topics:

  - Completed tasks

  - In-progress work

  - Risks or delays

  - Updated priorities

Monthly Stakeholder Review

- Duration: 45 – 60 minutes

- Purpose: Show working features and gather feedback

- Attendees: PM, Product Owner, Operators, Stakeholders

- Topics:

  - Demon of new features

  - High-level metrics (usage, defects, uptime)

  - Roadmap updates

  - Approval for next sprint direction

Communication Channels

1. Slack/Teams

- Daily communication

- Quick questions, blockers, updates

- Used for developer-to-developer communication

Email

- Weekly summaries

- Formal updates to operators and stakeholders

- Used for decisions, approvals, and documentation

Trello Board

- Real-time task tracking

- Shows To-Do, Doing, Done

- Used for sprint planning and daily stand-ups

Sprint Review Demo

- Monthly presentation of working features

- Used to gather feedback from stakeholders

Reports & Dashboards

- Occupancy metrics

- Payment summaries

- Bug/defect counts

- Used for executive-level visibility

Stakeholder Communication Strategy

Executives/Sponsors

- Receiving high-level summaries

- Focus on metrics: Revenue, uptime, usage

- Monthly email + dashboard snapshot

Operators

- Receive operational updates

- Focus on garage management features, reporting tools

- Weekly email + demo during stakeholder review

Developers

- Receive detailed technical tasks

- Focus on APIs, bugs, UI changes

- Daily stand-ups + Trello updates

Indirectly to Users

- Feedback collected through app usage metrics

- Issues reported though support channels

Escalation Path

Critical Issues (System is down/Some critical failure)

- Immediate Slack/Teams alert

- PM + Backend Lead respond within 15 minutes

- Stakeholders are notified within 1 hour

High-Impact Issues (Major bugs/Errors)

- Logged in Trello

- Assigned withing same day

- Included in next spring review

Low-Impact Issues (Minor bug/Error)

- Logged and prioritized normally

- Reviewed during weekly meeting

Documentation

Docs. Located

- Trello (tasks, sprint notes)

- Shared Drive (designs, API, important docs.)

- Email (formal approvals)

Update Frequency

- Weekly updates to shared documents

- Monthly updates to stakeholders dashboards

Nathaniel Medina

TLIM 3355 – Project Management Principles

10/8/2026

Homework 5

Version 1.4

Roles & Resources Smart Parking App:

- Project Manager – Alice Ramirez Skill Level: Intermediate Allocation: 15% FTE Estimated Hours: 60 hours

- Developer 1 – Bob Nguyen Skill Level: Intermediate Allocation: 50% FTE Estimated Hours: 200 hours

- Developer 2 – Carol Smith Skill Level: Intermediate Allocation: 50% FTE Estimated Hours: 200 hours

- QA Tester – Dan Patel Skill Level: Junior Allocation: 20% FTE Estimated Hours: 80 hours

- UX Designer – Emily Torres Skill Level: Intermediate Allocation: 15% FTE Estimated Hours: 60 hours

- DevOps Engineer – Madelynn Guevara Skill Level: Intermediate Allocation: 10% FTE Estimated Hours: 40 hours

Resource & Cost Plan:

| Role | Hours | Rate | Cost |
| --- | --- | --- | --- |
| Project Manager (Alice) | 60 | $167/hr | $10,000 |
| Developer 1 (Bob) | 200 | $150/hr | $30,00 |
| Developer 2 (Carol) | 200 | $150/hr | $30,000 |
| QA Tester (Dan) | 80 | $100/hr | $8,000 |
| UX Designer (Emily) | 60 | $100/hr | $6,000 |
| DevOps (Madelynn) | 40 | $150/hr | $6,000 |
| Labor Subtotal | 640 hours | — | $90,000 |

Infrastructure & Tools:

| Item | Cost |
| --- | --- |
| Cloud Hosting (3 months) | $4,000 |
| Licenses & Tools | $2,000 |
| API Usage (estimated) | $2,000 |
| Contingency (emergency funds) | $2,000 |

Infrastructure + Tools = $10,000

Monthly Cashflow Chart:

| Month | Labor | Infra | Licenses | Contingency | Total |
| --- | --- | --- | --- | --- | --- |
| Month 1 | $40,000 | $1,500 | $1,000 | $2,500 | $45,000 |
| Month 2 | $40,000 | $1,500 | $1,000 | $2,500 | $45,000 |
| Month 3 | $10,000 | $1,000 | $0 | $1,000 | $12,000 |
| Total | $90,000 | $4,000 | $2,000 | $6,000 | $102,000 |

RACI Matrix:

| Task | Developer | PM | QA | UX | DevOps | PO |
| --- | --- | --- | --- | --- | --- | --- |
| Requirements | C | C | I | C | I | A |
| Design | R | A | I | R | I | C |
| Implementation | A | C | I | C | I | C |
| System Testing | C | I | A | I | I | C |
| Deployment | I | C | C | I | A | I |

Nathaniel Medina

TLIM 3355 – Project Management Principles

10/15/2026

Homework 6

Version 1.5

Updated SRS:

Project: Smart Parking Platform

Version 1.5

10/15/2026

Nathaniel Medina

1. Introduction

1.1 Purpose

This updated SRS defines the current requirements for the Smart Parking Platform. It includes expanded functional and non-functional requirements based on project progress and feedback.

1.2 Scope

The Smart Parking Platform will provide real-time parking availability, an interactive map, reservation and payment features, operator dashboards, analytics, notifications, and API integrations. The system supports both web and mobile devices.

2. Overall Description

Users: Drivers, parking operators, city transportation staff, admins, tourists

System Environment: Web app, mobile app, cloud backend, third-party APIs

Constraints: City privacy laws, API limits, hosting costs, semester timeline

Assumptions: Internet access, GPS availability, modern mobile device compatibility

Functional Requirements (New):

FR9: The system shall allow users to view and manage past reservations

FR10: The system shall provide navigation directions to the selected parking spot

FR11: The system shall allow operators to adjust pricing dynamically

FR12: The system shall allow admins to manage user accounts and permissions

FR13: The system shall integrate with CI/CD pipelines to ensure tested code is deployed

FR14: The system shall log all major system events for auditing and troubleshooting

FR15: The system shall support multi-device sessions (user can switch devices)

FR16: The system shall provide a help/support section for users

FR17: The system shall allow users to filter parking spots by price, distance, and availability

FR18: The system shall allow operators to generate financial reports

FR19: The system shall support refund/cancellation workflows

FR20: The system shall allow users to update profile information

Non-Functional Requirements (New):

NFR6: The system shall encrypt all sensitive data (AES‑256 or equivalent)

NFR7: The system shall support mobile devices running iOS 14+ and Android 10+

NFR8: The system shall maintain response times under 2 seconds for all major actions

NFR9: The system shall support automated testing through CI/CD pipelines

NFR10: The system shall maintain 95% test coverage for critical features

NFR11: The system shall store logs for at least 90 days

NFR12: The system shall scale automatically during peak usage

NFR13: The system shall provide role‑based access control (RBAC)

NFR14: The system shall support secure API communication

NFR15: The system shall maintain compatibility with major browsers (Chrome, Safari, Edge, Firefox)

User Stories (New):

Drivers:

- As a driver, I want to create an account so that I can save my reservations.

- As a driver, I want to log in securely so that my personal information is protected.

- As a driver, I want to see real-time parking availability so that I can quickly find open spots.

- As a driver, I want an interactive map so that I can visually locate parking options.

- As a driver, I want to reserve a parking spot so that I know it will be available when I arrive.

- As a driver, I want to pay digitally so that I don’t need cash or kiosks.

- As a driver, I want to receive notifications so that I know when my parking time is about to expire.

- As a driver, I want to view my reservation history so that I can track my past parking usage.

- As a driver, I want navigation directions so that I can easily reach my reserved spot.

- As a driver, I want to filter parking spots by price, distance, and availability so that I can choose the best option.

Parking Operators:

- As an operator, I want to update parking spot availability so that drivers see accurate information.

- As an operator, I want to adjust pricing so that I can respond to demand or special events.

- As an operator, I want an occupancy dashboard so that I can monitor garage usage in real time.

- As an operator, I want to generate financial reports so that I can track revenue.

Admins:

- As an admin, I want to manage user accounts so that I can maintain system integrity.

- As an admin, I want to configure system settings so that the platform behaves correctly.

- As an admin, I want to review system logs so that I can troubleshoot issues.

System / Technical:

- As a system, I want to integrate with external APIs so that I can provide accurate map and sensor data.

- As a system, I want to run automated tests on each update so that deployments are stable.

- As a system, I want to encrypt sensitive data so that user information stays secure.

WBS (New):

1. Authentication & User Management

1.1 Registration

1.1.1 Input validation

1.1.2 Account creation

1.1.3 Email/SMS verification

1.2 Login

1.2.1 Credential verification

1.2.2 Session creation

1.2.3 Password reset

1.3 Profile Management

1.3.1 Update profile information

1.3.2 View reservation history

1.3.3 Multi‑device session support

1.4 Admin User Management

1.4.1 Manage user accounts

1.4.2 Assign roles/permissions

1.4.3 Suspend/restore accounts

2. Parking & Garage Management

2.1 Garage Setup

2.1.1 Add garage

2.1.2 Edit garage details

2.1.3 Remove garage

2.2 Spot Monitoring

2.2.1 Real-time occupancy tracking

2.2.2 Sensor/API updates

2.2.3 Error handling

2.3 Pricing Management

2.3.1 Update pricing

2.3.2 Dynamic pricing rules

2.3.3 Event-based pricing

2.4 Operator Dashboard

2.4.1 Occupancy dashboard

2.4.2 Financial dashboard

2.4.3 Garage performance analytics

3. Interactive Map & Navigation

3.1 Map Rendering

3.1.1 Load map tiles

3.1.2 Display parking overlays

3.1.3 Show availability indicators

3.2 Navigation

3.2.1 GPS integration

3.2.2 Route generation

3.2.3 Turn-by-turn directions

3.3 Filters & Search

3.3.1 Filter by price

3.3.2 Filter by distance

3.3.3 Filter by availability

4. Reservation & Payment System

4.1 Reservation Workflow

4.1.1 Select spot

4.1.2 Choose time/duration

4.1.3 Confirm reservation

4.2 Payment Processing

4.2.1 Payment gateway integration

4.2.2 Receipt generation

4.2.3 Refund/cancellation workflow

4.3 Notifications

4.3.1 Time remaining alerts

4.3.2 Expiration warnings

4.3.3 Payment confirmation

5. Reporting & Analytics

5.1 Occupancy Reports

5.1.1 Daily occupancy

5.1.2 Peak hours

5.1.3 Garage comparison

5.2 Financial Reports

5.2.1 Revenue summary

5.2.2 Payment logs

5.2.3 Export CSV/PDF

5.3 System Analytics

5.3.1 Usage trends

5.3.2 Error logs

5.3.3 System performance metrics

6. System Infrastructure & CI/CD

6.1 Source Control

6.1.1 GitHub repository setup

6.1.2 Branching strategy

6.1.3 Pull request workflow

6.2 CI/CD Pipeline

6.2.1 Automated builds

6.2.2 Automated testing

6.2.3 Deployment pipeline

6.3 Logging & Monitoring

6.3.1 Event logging

6.3.2 Error tracking

6.3.3 Performance monitoring

Projected Timeline (New):

Week 1–3: Requirements & Planning

- Finalize SRS (updated requirements, new FR/NFR)

- Research existing parking solutions

- Define user stories (updated set of 20)

- Identify constraints, assumptions, and risks

- Establish tools (Trello, GitHub, CI/CD pipeline setup)

- Create initial backlog

Milestone: Requirements Completed (End of Week 3)

Week 3–5: System & UI Design

- Create updated UI sketches

- Define system architecture

- Map out database schema

- Update WBS (Version 2.0)

- Update communication plan

- Prepare operator dashboard layout

- Update Gantt chart

Milestone: Design Approved (End of Week 5)

Week 5–7: Core Development

- Build authentication module

- Build reservation workflow

- Integrate payment gateway

- Implement notifications

- Develop interactive map (base version)

- Begin operator dashboard backend

Milestone: Core Features Functional (End of Week 7)

Week 7–9: Integration Phase

- Connect authentication → reservation → payment

- Integrate map overlays with real-time availability

- Connect operator dashboard to backend

- Fix integration bugs

- Update CI/CD pipeline with automated tests

Milestone: System Integrated (End of Week 9)

Week 9–11: System Validation

- Validate reservation accuracy

- Validate payment logs

- Validate operator dashboard data

- Performance testing (map updates 1–3 seconds)

- Security testing (privacy compliance)

Milestone: Validation Passed (End of Week 11)

Week 11–13: Beta Testing & Risk Review

- Conduct user testing

- Identify bugs and usability issues

- Update risk register

- Apply fixes and stability improvements

- Improve UI polish

Milestone: Beta Testing Complete (End of Week 13)

Week 13–16: Final Checks & Release

- Final UI polish

- Final performance tuning

- Final analytics/reporting setup

- Prepare release documentation

- Deploy initial version

- Monitor system logs

Milestone: Initial Release Ready (End of Week 16)

Gnatt Chart (New):

|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Require./Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| System Valid. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Beta/Risk Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Checks/Rel. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Backlog:

1. Authentication & User Management

- User registration

- Login system

- Password reset

- Profile management

- Reservation history

- Multi-device session support

- Admin user management

- Role/permission setup

2. Parking & Garage Management

- Add garage

- Edit garage details

- Remove garage

- Real-time occupancy tracking

- Sensor/API integration

- Error handling for spot updates

- Pricing updates

- Dynamic pricing rules

- Event-based pricing

3. Interactive Map & Navigation

- Map rendering

- Parking spot overlay

- Availability indicators

- GPS integration

- Route generation

- Turn-by-turn navigation

- Filters (price, distance, availability)

4. Reservation & Payment

- Select parking spot

- Choose time/duration

- Confirm reservation

- Payment gateway integration

- Receipt generation

- Refund/cancellation workflow

- Notification system

- Expiration warnings

5. Reporting & Analytics

- Daily occupancy reports

- Peak hour analytics

- Garage comparison

- Revenue summary

- Payment logs

- Export CSV/PDF

- Usage trends

- Error logs

- System performance metrics

6. System Infrastructure & CI/CD

- GitHub repository setup

- Branching strategy

- Pull request workflow

- Automated builds

- Automated testing

- Deployment pipeline

- Logging system

- Monitoring dashboard

Risks and Risk Register (New):

Technical Risks

- Sensor API instability

- Backend integration failures

- Map rendering performance issues

- Security vulnerabilities

- Data synchronization delays

- Payment gateway failures

Schedule Risks

- Backend delays

- UI redesign requests

- Dependency bottlenecks

- Unexpected bug volume

- CI/CD pipeline setup delays

Financial Risks

- Unexpected API costs

- Server hosting overages

- Additional team member costs

- Payment processor fees increasing

People Risks

- Team member turnover

- Skill gaps

- Poor communication

- Low morale/drive

Tools & Technology Risks (NEW)

- GitHub Actions pipeline failures

- Trello/Jira sync issues

- Third-party API rate limits

Security Risks (NEW)

- Data breaches

- Weak input validation

- Unauthorized access due to RBAC misconfiguration

| ID | Description | Probability (1-5) | Impact (1-5) | Score | Strategy | Owner | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Sensor API instability | 4 | 4 | 16 | Mitigate | Backend Lead | Add fallback sensor data |
| 2 | Backend integration failure | 3 | 5 | 15 | Mitigate | Full-stack Dev | Test in staging |
| 3 | Map rendering performance issues | 3 | 4 | 12 | Mitigate | UI/UX Lead | Optimize map layers |
| 4 | Payment gateway failure | 2 | 5 | 10 | Transfer | Finance/Devops | Add backup payment provider |
| 5 | CI/CD pipeline failures | 3 | 3 | 9 | Mitigate | Devops | Add automated test coverage |
| 6 | Unexpected API costs | 3 | 4 | 12 | Transfer | Finance | Move to cheaper tiers |
| 7 | Team member turnover | 2 | 5 | 10 | Accept | PM | Document tasks |
| 8 | Skill gaps | 3 | 3 | 9 | Mitigate | Team Lead | Provide training |
| 9 | Security vulnerabilities | 3 | 5 | 15 | Mitigate | Security Lead | Add validation + encryption |
| 10 | Third-party API rate limits | 4 | 2 | 8 | Mitigate | Backend Lead | Add caching + throttling |

Main Communication Plan (New):

1. Meeting Cadence

Daily Stand-Ups (10–15 minutes)

- Quick progress sync

- Blockers

- Assigned tasks

- Attendees: Developers, UI/UX, Backend, PM

Weekly Progress Meetings (30–45 minutes)

- Sprint review

- Updated priorities

- Risks or delays

- Attendees: Full team + Product Owner

Monthly Stakeholder Review (45–60 minutes)

- Demo of new features

- High-level metrics (usage, uptime, defects)

- Roadmap updates

- Attendees: PM, PO, Operators, Stakeholders

2. Communication Channels

Slack / Teams

- Daily communication

- Quick questions

- Bug alerts

- Dev-to-dev messaging

Email

- Weekly summaries

- Formal approvals

- Stakeholder updates

Trello Board

- Real-time task tracking

- Sprint planning

- Daily stand-up reference

GitHub

- Pull requests

- Code reviews

- CI/CD pipeline results

Reports & Dashboards

- Occupancy metrics

- Payment summaries

- Error logs

- Executive visibility

3. Stakeholder Communication Strategy

Executives / Sponsors

- Monthly dashboard snapshot

- Revenue, uptime, usage metrics

- High-level summaries

Operators

- Weekly operational updates

- Garage management changes

- Pricing adjustments

- Included in monthly demo

Developers

- Daily stand-ups

- Trello updates

- GitHub PR reviews

- CI/CD notifications

Users (Indirect)

- Feedback through app usage

- Support tickets

- Analytics trends

4. Escalation Path

Critical Issues (System down)

- Immediate Slack alert

- PM + Backend Lead respond within 15 minutes

- Stakeholders notified within 1 hour

High-Impact Issues (Major bugs)

- Logged in Trello

- Assigned same day

- Reviewed in weekly meeting

Low-Impact Issues (Minor bugs)

- Logged normally

- Prioritized during sprint planning

5. Documentation

- Trello: tasks, sprint notes

- Shared Drive: designs, API docs

- GitHub: code, PRs, CI/CD logs

- Email: approvals, formal communication

6. Update Frequency

- Weekly updates to shared documents

- Monthly updates to stakeholder dashboards

- Daily updates to Trello board

- Continuous updates via GitHub commits

Roles & Skill Levels (New):

Project Manager – Alice Ramirez

- Skill Level: Advanced (updated from Intermediate)

- Allocation: 15% FTE

- Estimated Hours: 60 hours

- Reason for update: Increased skill level due to expanded project scope and added CI/CD + reporting complexity.

Developer 1 – Bob Nguyen

- Skill Level: Advanced (updated from Intermediate)

- Allocation: 50% FTE

- Estimated Hours: 200 hours

- Reason for update: Handles core backend, payment integration, and API reliability.

Developer 2 – Carol Smith

- Skill Level: Intermediate → Advanced (updated)

- Allocation: 50% FTE

- Estimated Hours: 200 hours

- Reason for update: Responsible for interactive map, navigation, and UI complexity.

QA Tester – Dan Patel

- Skill Level: Junior → Intermediate (updated)

- Allocation: 20% FTE

- Estimated Hours: 80 hours

- Reason for update: Increased testing load due to added features (filters, navigation, analytics).

UX Designer – Emily Torres

- Skill Level: Intermediate → Advanced (updated)

- Allocation: 15% FTE

- Estimated Hours: 60 hours

- Reason for update: More complex UI flows (operator dashboard, reporting screens).

DevOps Engineer – Madelynn Guevara

- Skill Level: Intermediate → Advanced (updated)

- Allocation: 10% FTE

- Estimated Hours: 40 hours

- Reason for update: CI/CD pipeline, automated testing, monitoring, logging.

Labor Costs (New):

| Role | Hours | Rate | Cost |
| --- | --- | --- | --- |
| Project Manager (Alice) | 60 | $175/hr | $10,500 |
| Developer 1 (Bob) | 200 | $160/hr | $32,000 |
| Developer 2 (Carol) | 200 | $160/hr | $32,000 |
| QA Tester (Dan) | 80 | $110/hr | $8,800 |
| UX Designer (Emily) | 60 | $110/hr | $6,600 |
| DevOps Engineer (Madelynn) | 40 | $160/hr | $6,400 |
| Labor Subtotal | 640 hours | — | $96,300 |

Infrastructure & Tools:

| Item | Cost |
| --- | --- |
| Cloud Hosting (3 months) | $4,000 |
| Licenses & Tools | $2,000 |
| API Usage (estimated) | $2,000 |
| Contingency (emergency funds) | $2,000 |

Monthly Cashflow Chart (New):

| Month | Labor | Infra | Licenses | Contingency | Total |
| --- | --- | --- | --- | --- | --- |
| Month 1 | $45,000 | $1,500 | $1,000 | $2,500 | $50,000 |
| Month 2 | $40,000 | $1,500 | $1,000 | $2,500 | $45,000 |
| Month 3 | $11,300 | $1,000 | $0 | $1,000 | $13,300 |
| Total | $96,300 | $4,000 | $2,000 | $6,000 | $108,300 |

RACI Matrix (New):

| Task | Developer | PM | QA | UX | DevOps | PO |
| --- | --- | --- | --- | --- | --- | --- |
| Requirements | C | A | I | C | I | R |
| Design | R | A | I | R | I | C |
| Implementation | A | C | I | C | I | C |
| System Testing | C | I | A | I | I | C |
| Deployment | I | C | C | I | A | I |
| Reporting & Analytics | R | C | C | I | I | A |
| Operator Dashboard | R | C | I | R | I | A |
| Payment Processing | A | C | I | I | C | C |
| Map & Navigation | A | C | I | R | I | C |
| User Management | R | C | I | I | I | A |

Nathaniel Medina

TLIM 3355 – Project Management Principles

10/29/2026

Homework 7

Version 1.6

Stakeholder Power-Interest Grid:

| Stakeholder | Power | Interest | Management Strategy |
| --- | --- | --- | --- |
| City Transport. Department | High | High | Manage Closely |
| Project Sponsor | High | High | Manage Closely |
| Product Owner | High | High | Manage Closely |
| Instructor | High | Low | Keep Satisfied |
| Investors/Funding Partners | High | Low | Keep Satisfied |
| Parking Operators | Low | High | Keep Informed |
| Drivers/Users | Low | High | Keep Informed |
| Development Team | Low | High | Keep Informed |
| General Public | Low | Low | Monitor |
| Tourists/Visitors | Low | Low | Monitor |

Project Charter:

| Section | Details |
| --- | --- |
| Project Name | Smart Parking Platform |
| Project Purpose | Develop a platform that helps users locate, reserve, and pay for parking spaces in real time while providing tools for parking operators. |
| Problem Statement | Drivers spend unnecessary time searching for parking, causing congestion, wasted fuel, and frustration. Operators lack centralized tools for managing parking availability and reporting. |
| Business Case | Improve parking efficiency, reduce traffic congestion, increase parking utilization, and provide a better user experience. |
| Goals | • Provide real-time parking availability • Enable parking reservations • Support digital payments • Provide interactive navigation • Generate reports and analytics |
| Timeline | 16-week project lifecycle: Requirements → Design → Development → Integration → Validation → Testing → Release |
| Scope (Included) | Real-time availability, interactive maps, reservations, payments, notifications, reporting, analytics, operator dashboard |
| Scope (Excluded) | Hardware installation, sensor deployment, vehicle identification systems |
| Key Stakeholders | City Transportation Department, Project Sponsor, Product Owner, Drivers, Parking Operators, Development Team |
| Success Criteria | 99% uptime, accurate parking availability, reliable reservation system, secure payments, on-time delivery |
| Project Manager | Alice Ramirez |
| Project Team | Bob Nguyen, Carol Smith, Dan Patel, Emily Torres, Madelynn Guevara |

Team Charter:

| Section | Details |
| --- | --- |
| Misson | Develop a Smart Parking Platform that provides users with real-time parking information, reservations, and digital payments. |
| Scope | Plan, design, and manage development of the Smart Parking Platform. Physical hardware installation is outside project scope. |
| Goals | • Complete all project milestones • Deliver quality project documentation • Maintain effective communication • Deliver a reliable parking solution |
| Strengths & Skills | Project planning, software development, UI/UX design, testing, communication, documentation, cloud technologies. |
| Roles & Responsibilities | PM: Planning/Scheduling Developers: Software development UX: User interface design QA: Testing and validation DevOps: Deployment and infrastructure |
| Values | Accountability, professionalism, communication, collaboration, integrity. |
| Norms | Meet deadlines, communicate issues early, attend meetings, update Trello board regularly. |
| Communication Plan | Weekly team meetings, Trello for task tracking and version control, Teams/Email for communication. |
| Coordination Tools | Trello, Microsoft Teams, Email |
| Merics for Success | On-time assignments, completed milestones, updated project documents, successful final presentation. |
| Conflict Resolution | Discuss issues directly, seek compromise, escalate unresolved issues to the Project Manager. |
| Fun! | Celebrate completed milestones, recognize contributions, maintain positive team collaboration. |