Nathaniel Medina

TLIM 3355 – Project Management Principles

9/8/2026

Homework 1

Version 1.0

- Research: Existing Parking Solutions

  - ParkMobile

  - ParkWhiz

  - SpotHero

  - ParkHouston

  - Parking.com

    - How will our app be different:

      - We will have a full interactable map that includes live updates on availability

      - Our app will have real time tracking for how long your vehicle has and will be allowed to park

      - A reservation system with built in digital payment

      - A dashboard that allows users to see availability within their range and even pricing

      - Finally we’ll have privacy controls and of course city compliance

- Vision & Scope:

How This Project Was Acquired:

$oftware ¢orp was contracted by Houston to create a modern parking management system that brings together all available parking in Houston. We have a reputation for creating large-scale and reliable software, which is why Houston has chosen us.

Company Introduction:

Here at $oftare ¢orp, we have an endless budget and resources at our disposal. Not only that, but we have extensive experience in software development and amazing teams all over the board.

Project Vison:

The Smart Parking Platform will provide real time availability and reduce congestion inside parking garages/areas. This system will be supported on both web and mobile devices and have navigation services.

Project Scope:

- Real-time availability

- Interactive map

- Reservation and payments

- Operator dashboard (for updates and local parking nearby with pricing)

- Analytics and reporting

- Notifications and alerts

- API integration

Out of Scope:

- Hardware installation (cameras, sensors)

- Vehicle identification system

- SRS Draft:

- Software Requirements Specification

- Project: Smart Parking Platform

- Version 1.0

- Date: 9.08.2026

- 1. Introduction:

  - 1.1 Purpose

  - This document defines the requirements for Smart Parking Platform

- 1.2 Scope

  - This application will be able to provide real-time availability for users, an interactive map, a way to reserve spots and pay for them, and an operator dashboard for local spots and prices. We will also provide analytics and reports, notifications/alerts, and API integration

- 2. Overall Description

- -Users: Houston drivers, city transportation staff, workers, tourist

- -System Environment: Web-based and mobile applications

- -Constraints: City privacy laws, third party APIs, fixed semester timeline

- -Assumptions: Internet connection, GPS availability, and mobile device compatibility

- 3. Functional Requirements

- FR1: The system shall allow users to register and log in securely.

- FR2: The system shall display real-time availability for parking

- FR3: The system shall have an interactive map

- FR4: The system shall allow user to reserve spots

- FR5: The system shall process digital payments and process recipes

- FR6: The system shall send notification and alerts about time remaining

- FR7: The system shall provide an operator dashboard for local spots/updates

- FR8: The system shall generate analytics for the user

- 4. Non-Functional Requirements

- NFR1: The system shall support at least 250,000 concurrent users

- NFR2: The system shall update the map availability within 1 – 3 seconds

- NFR3: The system shall provide 99% uptime

- NFR4: The system shall process payments within 5 seconds

- NRF5: The system shall comply with city privacy and law

- 5. Use Case Example

- Title: Reserve Parking Spot

- Actor: Driver

- Precondition: User is logged in and GPS active

- Steps:

  - 1. User opens the map

  - 2. User finds vacant spot

  - 3. User reserves spot

  - 4. User pays

  - 5. System payment goes through

- Postcondition: Reservation is stored and visible

15 Use Case Examples:

1. Account creation

Actor: Driver

Precondition: User has not created an account

Steps:

- User opens app

- User clicks “Create Account”

- User enters information

- Systems takes data

- System creates an account

Postcondition: User now has an account

2. Login

Actor: Driver

Precondition: User has an existing account

Steps:

- User opens login screen

- User enters username and password

- System accepts data

Postcondition: User is logged in

3. View real-time availability

Actor: Driver

Precondition: User is logged in

Steps:

- User selects “Find Parking”

- System retrieves data and updates

- System displays available spaces nearby

Postcondition: User sees available spots

4. Use interactive map

Actor: Driver

Precondition: User is logged in
Steps:

- User opens map

- System loads parking spots

- System displays available parking spots

Postcondition: Users sees map with available parking

5. Reserve Parking Space

Actor: Driver

Precondition: User is logged in and available spots nearby

Steps:

- User selects parking spot

- Users selects time slot

- User confirms reservation

- System processes reservation

Postcondition: User reservation is stored

6. Digital payment

Actor: Driver

Precondition: User has a reservation

Steps:

- User selects payment method

- User enters payment details

- System processes payment

- System confirms transaction

Postcondition: Payment is completed

7. Receiving Notifications

Actor: Driver

Precondition: User has notifications active, has active reservation

Steps:

- System registers start time

- Systems send notification to user

Postcondition: User receives alert about time left

8. View Reservation History

Actor: Driver

Precondition: User is logged in

Steps:

- User opens “History”

- System retrieves past reservations in the past 90 days

- System displays list

Postcondition: User sees reservation history

9. Navigate to Parking Location

Actor: Driver

Precondition: User has a reservation

Steps

- User selects “Navigate”

- Systems opens navigation

- Directions are displayed

Postcondition: User is routed to location

10. View Occupancy Dashboard

Actor: Parking Management

Precondition: Parking Management is logged in

Steps

- Parking Management opens dashboard

- System retrieves occupancy data

- System displays analytics report

Postcondition: Parking Management sees real-time occupancy

11. Adjust Pricing

Actor: Parking Management

Precondition: Parking Management is logged in

Steps:

- Parking Management opens pricing settings

- Parking Management enters new pricing

- System prices update

Postcondition: New pricing is set

12. Generate Analytics Report

Actor: Parking Management

Precondition: Parking Management is logged in

Steps:

- Parking Management selects “Generate Report”

- System complies data

- System displays report

Postcondition: Parking Management receives report

13. Manager User Accounts

Actor: Admin

Precondition: Admin is logged in

Steps:

- Admin opens user management

- Admin selects user(s)

- Admin updates or modifies account

Postcondition: User account is updated

14. Configure System Settings

Actor: Admin

Precondition: Admin is logged in

Steps:

- Admin opens system settings

- Admin adjust configuration in settings

- System save changes

Postcondition: System settings get updated

15. Review Pay Logs

Actor: Payment Manager

Precondition: Payment Manager is logged in

Steps:

- Manager opens payment logs

- System retrieves transaction data

- System displays logs for manager

Postcondition: Manager revises payment history

Nathaniel Medina

TLIM 3355 – Project Management Principles

09/17/2026

Homework 2

Version 1.1

1. Work Breakdown Structure (WBS)

Smart Parking Platform – 3 Level Deep Structure

1. Authentication

1.1 Registration

1.1.1 Input validation

1.1.2 Account creation

1.1.3 Email/Message verification

1.2 Login

1.2.1 Credential verification

1.2.2 Session creation

1.2.3 Password reset

1.3 Session Management

1.3.1 Token generation

1.3.2 Auto logout

1.3.3 Multi-device handling

2. User & Operator Management

2.1 User Profiles

2.1.1 View profile

2.1.2 Edit profile

2.1.3 Delete profile/account

2.2 Operator Accounts

2.2.1 Create operator account

2.2.2 Assign garage

2.2.3 Permissions setup

2.3 Role Management
		2.3.1 Driver role

2.3.2 Operator role

2.3.3 Admin role

3. Parking & Garage Management

3.1 Garage Setup

3.1.1 Add garage

3.1.2 Edit garage details

3.1.3 Remove garage

3.2 Spot Monitoring

3.2.1 Real-time occupancy tracking

3.2.2 Update parking spot status

3.2.3 Error handling

3.3 Interactive Map

3.3.1 Map rendering

3.3.2 Spot availability overlay

3.3.3 GPS integration

4. Reservation & Payment

4.1 Reservation System

4.1.1 Select spot

4.1.2 Choose time/duration

4.1.3 Confirm reservation

4.2 Payment Processing

4.2.1 Process payments

4.2.2 Receipt generator/generation

4.2.3 Refund/cancellation integration

4.3 Notifications

4.3.1 Time remaining alerts

4.3.2 Expiration warnings

4.3.3 Payment confirmation

5. Reporting & Analytics

5.1 Occupancy Reports

5.1.1 Daily occupancy reports

5.1.2 Peak hours

5.1.3 Garage comparison

5.2 Financial Reports

5.2.1 Revenue summary

5.2.2 Payment logs

5.2.3 Export payment summary

5.3 System Analytics

5.3.1 Usage trends

5.3.2 Error logs

5.3.3 Basic system performance report

2. Timeline/Gantt Chart:

Project Duration: 16 weeks

Timeline:

Week 1-3: Requirements/Planning

- Define project goals

- Identify core features

- Outline any constraints and assumptions

Week 3-5: Design

- Create basic UI sketches/designs

- Plan databases structure

- Map out system flow

Week 5-7: Development

- Build authentication

- Implementation of parking/reservation features

- Add payment/notifications

Week 7-9: Integration

- Connect all modules together

- Ensure main user flows work end-to-end

- Fix issues cause by combining features together (minor bug fixes)

Week 9-11: System Validation

- Check data accuracy (spot reservations/times, ensure data is updating properly)

- Test loading and simple performance

- Confirm features work as intended

Week 11-13: Beta/Risk Testing

- Run user testing on core features

- Find bugs and errors

- Apply fixes and stability

Week 13-16: Final Checks/Release

- Polish UI and navigation

- Polish any core/side features

- Release and monitor

Milestones:

- Requirements completed (end of week 3)

- Design approved (end of week 5)

- Core features built (end of week 9)

- System integrated (end of week 11)

- Validation passed (end of week 13)

- Beta testing complete (end of week 15)

- Final release ready/initial release (end of week 16)

Gantt Chart:

|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Require./Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| System Valid. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Beta/Risk Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Checks/Rel. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Nathaniel Medina

TLIM 3355 – Project Management Principles

09/24/2026

Homework 3

Version 1.2

Trello Board:

Added needed information for my Trello board and posted necessary screenshots to my GitHub Public Repo.

Nathaniel Medina

TLIM 3355 – Project Management Principles

10/1/2026

Homework 4

Version 1.3

16 Risks for Technical, Schedule, Financial, and People:

Risk By Category:

Technical Risk:

- Sensor API Instability

- Backend Integration Failures

- Map Rendering Performance Issues

- Security Vulnerabilities

Schedule Risks:

- Backend Delays

- UI Redesign Requests

- Dependency Bottlenecks

- Team Availability Issues

Financial Risks:

- Unexpected Costs

- Server Hosting Expenses

- Hardware Costs

- Additional Team Member Costs

People Risk:

- Team Member Turnover

- Skills Gaps

- Poor Communication

- Low Morale/Drive

Risk Register Table

| ID | Description | Probability (1 – 5) | Impact (1 – 5) | Score | Response Strategy | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Sensor Instability | 4 | 4 | 16 | Mitigate | Backend Lead | Add fallback sensor data |
| 2 | Backend Integration Failure | 3 | 5 | 15 | Mitigate | Full-stack Dev | Test in staging |
| 3 | Backend Delays | 4 | 3 | 12 | Accept | PM | Adjust sprint workload |
| 4 | UI Redesign Requests | 3 | 3 | 9 | Mitigate | UI/UX | Freeze Changes After Sprint 2 |
| 5 | Unexpected API Costs | 3 | 4 | 12 | Transfer | Finance | Move To Cheaper Tiers |
| 6 | Server Hosting Overages | 2 | 4 | 8 | Mitigate | DevOps | Enable Autoscaling Limits |
| 7 | Team Member Turnover | 2 | 5 | 10 | Accept | PM | Document Tasks |
| 8 | Skill Gaps | 3 | 3 | 9 | Mitigate | Team Lead | Provide Training |
| 9 | Security Vulnerabilities | 3 | 5 | 15 | Mitigate | Security Lead | Add Validation |
| 10 | Dependency Bottlenecks | 4 | 2 | 8 | Accept | Backend Lead | Monitor API Uptime |

Communication Plan

1. Meeting Times

Daily Update:

- Duration: 10 – 15 minutes

- Purpose: Quick sync on progress and blockers

- Attendees: Developers, UI/UX, Backend and PM

- Format:

  - What was done yesterday

  - What will be done today

  - Any blockers

Week Progress Meetings

- Duration: 30 – 45 minutes

- Purpose: Review sprint progress, adjust workload

- Attendees: Full team + Product Owner

- Topics:

  - Completed tasks

  - In-progress work

  - Risks or delays

  - Updated priorities

Monthly Stakeholder Review

- Duration: 45 – 60 minutes

- Purpose: Show working features and gather feedback

- Attendees: PM, Product Owner, Operators, Stakeholders

- Topics:

  - Demon of new features

  - High-level metrics (usage, defects, uptime)

  - Roadmap updates

  - Approval for next sprint direction

Communication Channels

1. Slack/Teams

- Daily communication

- Quick questions, blockers, updates

- Used for developer-to-developer communication

Email

- Weekly summaries

- Formal updates to operators and stakeholders

- Used for decisions, approvals, and documentation

Trello Board

- Real-time task tracking

- Shows To-Do, Doing, Done

- Used for sprint planning and daily stand-ups

Sprint Review Demo

- Monthly presentation of working features

- Used to gather feedback from stakeholders

Reports & Dashboards

- Occupancy metrics

- Payment summaries

- Bug/defect counts

- Used for executive-level visibility

Stakeholder Communication Strategy

Executives/Sponsors

- Receiving high-level summaries

- Focus on metrics: Revenue, uptime, usage

- Monthly email + dashboard snapshot

Operators

- Receive operational updates

- Focus on garage management features, reporting tools

- Weekly email + demo during stakeholder review

Developers

- Receive detailed technical tasks

- Focus on APIs, bugs, UI changes

- Daily stand-ups + Trello updates

Indirectly to Users

- Feedback collected through app usage metrics

- Issues reported though support channels

Escalation Path

Critical Issues (System is down/Some critical failure)

- Immediate Slack/Teams alert

- PM + Backend Lead respond within 15 minutes

- Stakeholders are notified within 1 hour

High-Impact Issues (Major bugs/Errors)

- Logged in Trello

- Assigned withing same day

- Included in next spring review

Low-Impact Issues (Minor bug/Error)

- Logged and prioritized normally

- Reviewed during weekly meeting

Documentation

Docs. Located

- Trello (tasks, sprint notes)

- Shared Drive (designs, API, important docs.)

- Email (formal approvals)

Update Frequency

- Weekly updates to shared documents

- Monthly updates to stakeholders dashboards

Nathaniel Medina

TLIM 3355 – Project Management Principles

10/8/2026

Homework 5

Version 1.4

Roles & Resources Smart Parking App:

- Project Manager – Alice Ramirez Skill Level: Intermediate Allocation: 15% FTE Estimated Hours: 60 hours

- Developer 1 – Bob Nguyen Skill Level: Intermediate Allocation: 50% FTE Estimated Hours: 200 hours

- Developer 2 – Carol Smith Skill Level: Intermediate Allocation: 50% FTE Estimated Hours: 200 hours

- QA Tester – Dan Patel Skill Level: Junior Allocation: 20% FTE Estimated Hours: 80 hours

- UX Designer – Emily Torres Skill Level: Intermediate Allocation: 15% FTE Estimated Hours: 60 hours

- DevOps Engineer – Madelynn Guevara Skill Level: Intermediate Allocation: 10% FTE Estimated Hours: 40 hours

Resource & Cost Plan:

| Role | Hours | Rate | Cost |
| --- | --- | --- | --- |
| Project Manager (Alice) | 60 | $167/hr | $10,000 |
| Developer 1 (Bob) | 200 | $150/hr | $30,00 |
| Developer 2 (Carol) | 200 | $150/hr | $30,000 |
| QA Tester (Dan) | 80 | $100/hr | $8,000 |
| UX Designer (Emily) | 60 | $100/hr | $6,000 |
| DevOps (Madelynn) | 40 | $150/hr | $6,000 |
| Labor Subtotal | 640 hours | — | $90,000 |

Infrastructure & Tools:

| Item | Cost |
| --- | --- |
| Cloud Hosting (3 months) | $4,000 |
| Licenses & Tools | $2,000 |
| API Usage (estimated) | $2,000 |
| Contingency (emergency funds) | $2,000 |

Infrastructure + Tools = $10,000

Monthly Cashflow Chart:

| Month | Labor | Infra | Licenses | Contingency | Total |
| --- | --- | --- | --- | --- | --- |
| Month 1 | $40,000 | $1,500 | $1,000 | $2,500 | $45,000 |
| Month 2 | $40,000 | $1,500 | $1,000 | $2,500 | $45,000 |
| Month 3 | $10,000 | $1,000 | $0 | $1,000 | $12,000 |
| Total | $90,000 | $4,000 | $2,000 | $6,000 | $102,000 |

RACI Matrix:

| Task | Developer | PM | QA | UX | DevOps | PO |
| --- | --- | --- | --- | --- | --- | --- |
| Requirements | C | C | I | C | I | A |
| Design | R | A | I | R | I | C |
| Implementation | A | C | I | C | I | C |
| System Testing | C | I | A | I | I | C |
| Deployment | I | C | C | I | A | I |